## DMAC Workplan
[6 empty] | 2020 | [11 empty] | 2021
Activity | Responsible | Results | Deliverables / Milestones | Notes | Status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1) Diagnostic
1.1) Diagnostic visit prep
Develop agenda and materials and share via introductory call
1.2) Diagnostic visit
Conduct a diagnostic visit to assess readiness and align on project goals and scope
Agree initial scope
Draft workplan
1.3) Weekly engagement to build capacity for data-driven product development
Develop agenda and materials
Project governance and regular calls
2) Market research and data analysis
2.1) Prep and Pre-Product Workshop Research
External data landscaping
Segmentation and analysis of internal customer data
Conduct research with target customers using HCD/lean research methodology (existing products customers, if applicable)
Debrief customer research, integrate findings with internal/external data analysis, and feed into product definition
2.2) Strategic use of data in the customer journey of the product
Workshop 1: Conduct workshop on the strategic use of data to refine product concept, align on processes and data required at each step
2.3) Process mapping and data inventory to support data-driven product design by maximizing usable 'digital footprint'
Define the data points for the product
Initial process mapping and data inventory
Finalize process mapping and data inventory
Identify 3rd party partnerships required for data streams as input into product operations
Define specific product business requirements and KPIs for project-sepcific dashboard, and reports
3) Product Build
3.1) Propose Product structure
Develop product structure document based on strategic use of data workshop, focusing on a specific specific sub-segment of the target market
3.2) Business case
Develop Business Case with full forecasts and profitability analysis
3.4) Product Structure Validation & Production
Focus groups to test proposed product structure
Revise business case
Workshop 2: Final discussions and finalization of product structure
Finalize product structure document and business case
Develop integrated product development workplan
Develop product policies and procedures, led by the FSP
Implement system solutions for new product
4) Product Testing
Develop pilot implementation plan
Develop customer engagement strategy and go to market plan
Develop product testing plan
Conduct product beta test
Final modifications to product based on beta test results
Develop staff training and customer engagement materials and lead staff TOT
5) Pilot launch and Monitoring
Product pilot launch
Monitor usage KPIs through product dashboard
Solicit user feedback
Pilot evaluation
Close project